## Sheet1
Day | Time Slot | Tasks(or schedule) | Outcome / Deliverables | State
2025-07-28 | 9:00 AM – 12:00 PM | Initialize frontend (Expo with TypeScript), create folder structure | /mobile initialized with navigation, folders scaffolded | Done
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | Initialize backend (Express + Prisma), define PostgreSQL schema in schema.prisma | /backend initialized, schema designed, .env and DB config done | Done
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Run `prisma migrate dev`, test DB connection, commit to GitHub | Local DB working, project base committed | Done
4:00 AM – 7:00 AM
2025-07-29 | 9:00 AM – 12:00 PM | Create auth routes: register, login, JWT handling, role-based middleware | auth.controller.ts and middleware complete | Done
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | Create workout routes (CRUD), protected with JWT, use Prisma | All core workout routes (user only) work via Postman | Done
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Create admin routes: GET /users, DELETE /users/:id, GET /analytics | Admin-level API routes functioning | Done
4:00 AM – 7:00 AM
2025-07-30 | 9:00 AM – 12:00 PM | Build Login & Register screens, set up navigation (AuthStack vs AppStack) | Auth navigation logic in place, UI for forms built
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | Integrate API with login/register, store token with AsyncStorage | Authenticated state persists between app reloads
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Design welcome/onboarding screens | Smooth entry experience for new users
4:00 AM – 7:00 AM
2025-07-31 | 9:00 AM – 12:00 PM | Build workout logging screen (form + submit to backend), show success/error feedback | /workouts POST connected from mobile
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | Build workout history screen with FlatList | Logged workouts shown in chronological order
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Integrate chart component using Victory Native or react-native-svg-charts | Weekly or monthly activity summary graph
4:00 AM – 7:00 AM
2025-08-01 | 9:00 AM – 12:00 PM | Create admin-only navigation and conditional rendering | Admin dashboard skeleton added
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | List users, delete users/logs from admin dashboard | /admin/users and /admin/analytics connected to UI
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Polish styling, add reusable components, mobile spacing | Visual consistency across screens
4:00 AM – 7:00 AM
2025-08-02 | 9:00 AM – 12:00 PM | Write unit tests (backend: Jest, frontend: RTL), handle edge cases | Key units tested and validated
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | Manual QA: iOS & Android simulators, form validation, role-based UI | Core features validated across platforms
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Fix bugs, optimize UI interactions | Clean UX, reduced bugs before delivery
4:00 AM – 7:00 AM
2025-08-03 | 9:00 AM – 12:00 PM | Deploy backend to Railway or Render, test from mobile | Production backend live, connected to app
12:00 PM – 4:30 PM
| 4:30 PM – 7:00 PM | Finalize docs: README.md, test-plan.md, deployment-guide.md, admin-guide.md | Complete documentation in Markdown/PDF
10:00 PM – 2:00 AM
| 2:00 AM – 4:00 AM | Tag release (v1.0.0), record 2–3 min walkthrough video (optional), create zip/share links | Final delivery version ready for handoff or showcase
4:00 AM – 7:00 AM